## Slide 1: Land Mobile Radio System Upgrade Project Status Report
Bob Schwent
WSP Electronic Services Division
State Interoperability Executive Committee (SIEC)
February 21, 2019

## Slide 2: Project Status Report
2003 – WSP partners with the US Department of Justice (DOJ) to deploy the Integrated Wireless Network (IWN) as a pilot project.
2005 – WSP and DOJ expand successful pilot to include Eastern Washington
2007 – WSP installs two trunked radio sites on the IWN system as a P25 technology pilot for WSP.
2009 – WSP upgrades 5 console positions in Marysville WSP facility on the IWN system to support the 2010 Olympic communications.
2011 – WSP joins the IWN system at the request of DOJ to improve coverage and interoperability as part of the WSP Narrowband Project.
  WSP becomes zone 2 of the IWN system using a second Master Site through an Inter-zone link (single system architecture).
  - MOU states that when technology supports it WSP will change to an ISSI connection and split the systems.
2015 – DOJ communications are consolidated under the FBI.
2018 – FBI and WSP agree to upgrade the system Master Sites and implement an ISSI connection in place of the Inter-zone link (two system architecture with cross-system roaming).
Land Mobile Radio System Upgrade Project (LMRSUP)
Project Background

## Slide 3: Project Status Report
Install new WSP Master Site at the State Data Center in Quincy, WA.
  Upgraded software and hardware to 7.17.2 release version
  Meets OCIO requirements to house the network core in a State Data Center
Configure and install ISSI 8000 connection between FBI and WSP Master Sites.
  Addresses SAO recommendation regarding interdependence with IWN
Update all WSP radios with the new system ID.
  - Will impact all users of the WSP trunked radio system
Upgrade NICE radio and telephony logging system.
  - Meets OCIO requirements to retire Windows Server 2003
Upgrade all WSP dispatch consoles.
Update security and Information Assurance plans and documentation.
Upgrade all trunking infrastructure.
Cutover system to new Master Site.
Decommission old WSP Master Site.
Land Mobile Radio System Upgrade Project (LMRSUP)
Project Scope

## Slide 4: Project Status Report
< Project Information >
Executive Sponsors: Assistant Chief Marc Lamoreaux Project Sponsor: Bob Schwent
Assistant Chief Jeff Sass
Tom Wallace, CTO
Project Manager: Dave Pratt
< Project Reporting >
Reporting Start Date: August 16, 2018 Reporting End Date: October 18, 2018
< Schedule and Budget >
Scope | Schedule | Budget | Quality
On Plan | Possible Variance | On Plan | On Plan
Expenditures | To Date
Project Budget | $1,631,995
Planned Cost to Date | $504,995
Actual Cost to Date | $497,715
Variance | $7,280
Remaining Contingency | $98,657
Land Mobile Radio System Upgrade Project (LMRSUP)

## Slide 5: Project Status Report
Land Mobile Radio System Upgrade Project (LMRSUP)
Task Name | Planned Start | Planned Finish | Status
Project Start Date | 6/1/2018 |  | Project Started
Contract Award - Part A (FBI) | 7/20/2018 | 7/20/2018 | Complete
Contract Award - Part B (WSP) | 8/1/2018 | 9/11/2018 | Complete
Kickoff Meeting - Part A/B | 8/1/2018 | 8/1/2018 | Complete
Critical Design Review | 9/25/2018 | 9/26/2018 | Complete
Subscriber Update (Radios) | 8/20/2018 | 4/30/2019 | Underway
Staging Part A and Part B | 1/10/2018 | 2/6/2019 | Complete
Install and cable new Core and NICE Equipment | 2/20//2019 | 3/5/2019 | Pending
Core Equipment and ISSI 8000 Link In-place and Optimized | 3/12/2019 | 3/12/2019 | Pending
Key Project Milestones

## Slide 6: Project Status Report
Task Name | Planned Start | Planned Finish | Status
Link RF Sites to new Core | 3/13/2019 | 3/19/20019 | Pending
Optimize System | 3/20/2019 | 3/26/2019 | Pending
Perform System Testing | 3/27/2019 | 4/2/2019 | Pending
Cutover to New Core at Quincy Data Ctr. | Being Rescheduled | Being Rescheduled | Being Rescheduled
District 1-8 Cutover | Being Rescheduled | Being Rescheduled | Being Rescheduled
Schedule Contingency | Being Rescheduled | Being Rescheduled | Being Rescheduled
Project Complete |  | 6/30/2019 | Pending
Suspense Date for Core Relocation to State Data Center to Satisfy OCIO Policy 184 Waiver |  | 8/31/2019 | Pending
Key Project Milestones Cont’d
Land Mobile Radio System Upgrade Project (LMRSUP)

## Slide 7: Project Status Report
ID | Priority | Owner | Risk Description | Risk Response
15 | 1 – High | Dave Pratt | - Once the core upgrade project is completed, Troopers working in District 2 on the trunked radio system using the auto-roaming function may perceive a loss of communications when they move into four coverage areas served by Department of Justice (DOJ) transmission sites not upgraded as part of the project. - To avoid a loss of radio communications, Troopers must manually change their radios to an alternate channel when they move into those areas, and change back again when they return to the auto-roaming coverage area. This situation could pose a risk to Troopers working high-intensity, fast-paced incidents or who are unfamiliar with their beats. | - Accept the Risk - Set clear expectations in the districts relying upon automatic roaming, to manually roam into those areas covered by Quantar-based IWN sites. Include this information in the Trooper training package developed for the project.
Key Risks
Land Mobile Radio System Upgrade Project (LMRSUP)

## Slide 8: Project Status Report
ID | Priority | Owner | Risk Description | Risk Response
16 | 1 – High | Dave Pratt & Jameson Keck & Ron Chapman | During the government shutdown, the FBI's radio shop was furloughed. As a result, key project tasks are lagging for the FBI portion of the project. The FBI is scrubbing their schedule to identify the impact and a realistic timeline for final system cutover. Impact is most likely to be seen in a schedule slip for final cutover and marginal cost impact to the WSP effort. | - Accept the Risk - Work with the FBI and Motorola to develop a realistic estimate of the cutover process. Move ahead with WSP project work as currently scheduled, without impact to the schedule.
19 | 1 – High | Dave Pratt & Bob Schwent | - The System Administrator for the LMR System has submitted his resignation for late March 2019, a month and a half before cutover to the upgraded core. This individual possesses unique corporate and technical knowledge that is not held by others. His loss presents a significant risk to the project. | - Mitigate the Risk - Train a replacement, starting as soon as possible. ​Contract with Motorola to bring on a temporary, skilled resource to supplement the project team's capabilities.
Key Risks Cont’d
Land Mobile Radio System Upgrade Project (LMRSUP)

## Slide 9: Project Status Report
Project Schedule
Land Mobile Radio System Upgrade Project (LMRSUP)

## Slide 10
Questions?
Bob Schwent
(360) 534-0601
robert.schwent@wsp.wa.gov